QUAD360

PHASE 1 EXECUTION PLAN

Building to 3% Market Share in 6 Months

| Period | Month 1–6 (Immediate Launch through End-of-Month 6) |
| --- | --- |
| Target | 1.2M signed-up users, 400k active users, 3% market share |
| Prepared by | Quadri Abiodun, Co-Founder & CEO, Quad360 |
| Document | PHASE_1_EXECUTION_PLAN.md |
| Date | June 27, 2026 |
| Classification | Strategic / Confidential |

# TABLE OF CONTENTS

1. Executive Summary

2. Critical Path Dependencies

3. Month 1: Credibility + Foundation

4. Month 2: Activation & Community Infiltration

5. Month 3–4: Scale & Ecosystem Solidification

6. Month 5–6: Acceleration & First Milestones

7. Phase 1 Success Criteria

8. Resource Allocation

9. Budget Allocation

10. Contingency Plans

11. Weekly Reporting Cadence

# Executive Summary

Phase 1 represents the foundation-building stage of Quad360's market dominance strategy. Over 6 months, we will establish credibility through bank partnerships, activate community channels, and prove viral mechanics. By end of Phase 1, we target 1.2M signups (3% market share) on our path to 60% dominance.

Key Outcomes by End of Phase 1:

✓ 32,000–41,000 cumulative signups

✓ 8,000–12,000 Daily Active Users (DAU)

✓ 500–1,000 paid plan conversions (₦2.5k/month)

✓ 3 viral loops activated (referral, invoices, payment links)

✓ Zenith Bank pilot validated with 5,000+ users

✓ 15 market association partnerships operational

✓ ₦1.25M–₦2.5M Monthly Recurring Revenue (MRR)

✓ >40% Day-30 retention (habit formation)

✓ 50%+ of growth from organic/network effects (not paid acquisition)

Total Phase 1 Investment: ₦28M over 6 months
Expected CAC (Customer Acquisition Cost): ₦680–875 per signup
Expected LTV (Lifetime Value): ₦30,000 per paid user (12-month horizon)

# Critical Path Dependencies

Before any external-facing activity, these foundation items must be operational. Any delay in these blocks the entire Phase 1 timeline.

## Week 1–2: Foundation Setup

Zenith Bank Partnership Agreement Signed
Owner: Quadri (CEO) + Partnerships manager
Deliverable: Signed pilot agreement committing 500 SMEs, duration 90 days
Risk: HIGH — if Zenith delays, entire bank distribution plan delays
Contingency: Parallel track Access Bank conversation

Platform Stability Audit
Owner: Engineering lead
Deliverable: Zero known critical bugs, 99.5% uptime SLA met, security audit complete
Risk: HIGH — crashes on launch destroy brand reputation
Contingency: Load test to 10k concurrent users before public announcement

Customer Support Ticketing System Live
Owner: Operations manager
Deliverable: Zendesk/similar ticketing + WhatsApp support channel
Risk: MEDIUM — slow support = churn
Contingency: Pre-hire 3 support staff before launch week

Analytics & KPI Dashboard Live
Owner: Product + Analytics
Deliverable: Real-time dashboard: DAU, signups, retention, payments, errors
Risk: MEDIUM — no visibility = flying blind
Contingency: Manual Sheets tracking if automated dashboard delayed

Referral Program Infrastructure
Owner: Engineering
Deliverable: Referral codes, tracking, reward distribution automated
Risk: MEDIUM — broken referral = kills viral growth
Contingency: Manual referral tracking via spreadsheet (less scalable, but functional)

# MONTH 1: Credibility + Foundation

Month 1 focuses on internal readiness and soft launch validation. We prove the product works, build support infrastructure, and validate that early users find value.

## Week 1: Internal Readiness

| Task | Owner | Timeline | Success Criteria |
| --- | --- | --- | --- |
| Zenith Bank Pilot Kickoff | Quadri + Partnerships | 1 week | Final signed agreement + 500 SME contact list |
| Platform Load Testing | Engineering | 3 days | 10k concurrent users, <500ms response time |
| Customer Support Setup | Operations | 3 days | WhatsApp + Zendesk, 3 trained staff |
| Analytics Dashboard Launch | Product | 3 days | Real-time KPI tracking for internal team |

## Week 2: Go-To-Market Preparation

| Task | Owner | Timeline | Deliverable |
| --- | --- | --- | --- |
| Zenith Communications Kit | Marketing | 2 days | Email + WhatsApp + SMS templates (3 variants) |
| Micro-Influencer Briefing | Marketing | 3 days | 30 influencers, briefing doc, access codes |
| Community Partnership Pipeline | Growth | 5 days | 10 market associations, MOUs drafted |
| WhatsApp Broadcast Setup | Growth | 2 days | 500 contacts, segmented by audience |

## Week 3–4: Soft Launch (500-Person Pilot)

| Task | Owner | Timeline | Expected Result |
| --- | --- | --- | --- |
| Zenith SME Pilot Launch | Product + Growth | 1 week | 500 users, 25–30% signup rate |
| Micro-Influencer Content | Marketing | 1 week | 30 TikToks + 30 Reels, 2M+ reach |
| Market Association Events | Growth | 2 weeks | 3 demo events, 150–300 signups |
| Church Business Groups | Growth | Ongoing | 200 WhatsApp contacts, 1 broadcast/week |

## Month 1 Success Metrics

| Metric | Target |
| --- | --- |
| Zenith pilot MOA signed | 1 ✓ |
| Platform stress test passed | Yes ✓ |
| Support team trained | 3 people |
| Analytics dashboard live | Yes ✓ |
| Influencer briefing packs sent | 30 influencers |
| Market association MOUs | 3+ signed |
| Cumulative signups | 500–1,000 |
| DAU (Daily Active Users) | 150–300 |
| D7 retention (% back on day 7) | >25% |

Month 1 Expected Outcomes:
✓ 500–1,000 cumulative signups
✓ 150–300 DAU
✓ 0 critical platform issues
✓ 3 market association partnerships locked in
✓ 30 micro-influencers creating content

# MONTH 2: Activation & Community Infiltration

Month 2 shifts from soft launch to full community mobilization. We activate viral loops, scale community events, and prove organic growth is working.

## Key Initiatives

| Initiative | Description | Expected Result |
| --- | --- | --- |
| Market Day Demo Tour | Weekly on-the-ground demos at markets (Alaba, Balogun, Computer Village) | 20–30 signups/event |
| Church Fellowship Program | Partner with 20 church business fellowships | 240–400 signups per 10 churches |
| Influencer Wave 1 Amplification | 30 influencers post 60 pieces of content | 2M+ impressions, 10k clicks |
| WhatsApp Educational Series | 4-week broadcast series (1x/week) | 25–40 signups per broadcast |
| Referral Program Launch | Refer 1 → both get 1 month free | 0.3 k-factor, 600 new users |

## Month 2 Success Metrics

| Metric | Target |
| --- | --- |
| Market day events held | 8 |
| Direct signups from market days | 160–320 |
| Church partnerships launched | 10 |
| Church workshop signups | 200–400 |
| Influencer content pieces | 60 |
| Influencer content reach | 2M impressions |
| WhatsApp broadcasts sent | 4 |
| Referral program active users | 1,500+ |
| Month 2 signups | 3,000–4,000 |
| Cumulative signups (M1+M2) | 4,000–5,000 |
| DAU | 800–1,200 |
| D7 retention | >30% |

Month 2 Expected Outcomes:
✓ 3,000–4,000 new signups (cumulative: 4k–5k)
✓ 800–1,200 DAU
✓ 3 viral loops activated (referral, invoices, payment links)
✓ 10 church partnerships operational
✓ 8 market day events completed

# MONTH 3–4: Scale & Ecosystem Solidification

Month 3–4 focuses on validation of pilot results and transition to paid acquisition. Bank partnership scales from 500 to 5,000 users. Paid social campaigns launch.

## Zenith Bank Pilot Ramp

Pilot Month 1 Results (Week 9–10): Measure 500 Zenith SMEs' engagement: activation rate (target >50%), D7 retention (target >30%), feature adoption, data quality

Expansion Phase (Week 11–16): If pilot succeeds, expand from 500 to 5,000 Zenith SME users via email + in-app announcements

## Broader Community Expansion

| Initiative | Target | Expected Result |
| --- | --- | --- |
| Market Association Coalition | Expand from 3 to 15 associations | 3k potential users |
| Paid Social Campaign | Instagram + Facebook, ₦500k budget | 2,500–3,000 signups |
| Influencer Wave 2 | 30 additional micro-influencers | 2M+ impressions, 3–4k signups |
| Ecosystem Integration Prep | FIRS tax filing + Payroll beta test | Ready for Phase 2 |

## Month 3–4 Success Metrics

| Metric | Target |
| --- | --- |
| Zenith pilot activation rate | >50% |
| Zenith pilot D7 retention | >30% |
| Zenith expansion to | 5,000 users |
| Market association partnerships | 15 total |
| Paid social signups/month | 2,500–3,000 |
| Influencer Wave 2 reach | 2M+ impressions |
| Month 3–4 signups combined | 8,000–12,000 |
| Cumulative signups (M1–M4) | 12,000–17,000 |
| DAU | 3,000–5,000 |
| Paid plan conversion rate | 2–3% of DAU |
| D7 retention | >35% |

# MONTH 5–6: Acceleration & First Milestones

Month 5–6 focuses on viral loop maturation and first revenue generation. Organic growth should exceed paid acquisition. Paid tier conversions accelerate.

## Viral Loop Maturation

| Loop | Expected Result |
| --- | --- |
| Referral Program Analysis | 0.3–0.5 k-factor, 4–5k new users from referral |
| Invoice Loop Optimization | 5–10% recipients download, 20% convert to signup |
| Payment Link Loop | 10–20% of payers explore app, 2–3k signups |
| Network Effects Dashboard | Organic growth should be 50%+ of total signups |

## Paid Acquisition Scale

Budget increase from ₦500k to ₦2M/month based on proven CPA <₦50k with ROAS >2x

| Platform | Budget | Expected Signups/Month |
| --- | --- | --- |
| Instagram | ₦1M | 2,000–2,500 |
| Facebook | ₦500k | 1,000–1,500 |
| TikTok (new) | ₦500k | 1,000–1,500 |
| Total | ₦2M | 4,000–5,000 |

## Product Completeness

| Feature | Timeline | Expected Impact |
| --- | --- | --- |
| Payroll Feature General Release | Week 19 | 15% of users with staff enable (1,000+) |
| Cash Flow Forecasting Enhancement | Week 21 | Increased engagement, better stickiness |

## Month 5–6 Success Metrics

| Metric | Target |
| --- | --- |
| Referral program new users | 4,000–5,000 |
| Invoice loop new users | 1,000–2,000 |
| Organic growth % of total | >50% |
| Paid social spend/month | ₦2M |
| Paid social signups/month | 4,000–5,000 |
| Official Quad360 social followers | 10k–20k |
| Payroll feature active users | 1,000+ |
| Month 5–6 combined signups | 10,000–12,000 |
| CUMULATIVE SIGNUPS (M1–M6) | 32,000–41,000 |
| DAU (end of M6) | 8,000–12,000 |
| Paid conversions cumulative | 500–1,000 users |
| MRR (end of M6) | ₦1.25M–₦2.5M |
| D30 retention | >40% |

# Phase 1 Success Criteria (End of Month 6)

## User Metrics

32,000–41,000 cumulative signups (on track to 1.2M by end of Year 1)

8,000–12,000 DAU (target: 25–30% of signups)

>40% D30 retention (users finding value and returning)

500–1,000 paid conversions (2–3% of DAU)

₦1.25M–₦2.5M MRR (enough to cover costs + reinvest)

## Engagement Metrics

3+ daily transactions per DAU (frequency = habit formation)

5+ invoices created per active SME per month

Payroll adoption: 10%+ of SMEs with staff using feature

## Viral Metrics

Referral k-factor: >0.3 (organic growth loop working)

Invoice loop conversion: 5%+ of recipients → signup

Payment link loop: 2,000+ signups

Organic growth: 50%+ of new signups from network effects

## Partnership Metrics

Zenith Bank: 5,000+ SMEs using Quad360 via bank channel

Market associations: 15+ partnerships operational

Influencers: 60 pieces of content, 5M+ cumulative impressions

Community: 1,000+ direct signups from in-person market days

## Platform Metrics

Uptime: 99.5%+ (zero major outages)

Error rate: <0.5% of transactions

Data integrity: 100% transaction accuracy on reconciliation

Security: Passed third-party penetration test

## Financial Health

CAC (Customer Acquisition Cost): <₦50k

LTV (Lifetime Value): ₦30k for monthly users

Payback period: <12 months

Unit economics: Positive for paid tier users

# Resource Allocation (Phase 1)

## Team Structure

| Role | Responsibility | Headcount |
| --- | --- | --- |
| CEO/Founder | Zenith partnership, board updates, strategic decisions | 1 |
| Product Lead | Feature prioritization, roadmap, payroll/tax prep | 1 |
| Growth Lead | Community partnerships, market events, influencers, paid social | 1 |
| Marketing Lead | Content creation, social media, messaging, PR | 1 |
| Engineering Lead | Platform stability, integrations, performance | 2 |
| Operations Lead | Support ticketing, SLA management, partner onboarding | 1 |
| Data/Analytics | Real-time dashboards, KPI tracking, weekly reports | 1 |

Total headcount for Phase 1: 8–10 people

# Budget Allocation (6 Months)

| Category | Monthly Avg | Total 6-Month | Notes |
| --- | --- | --- | --- |
| Personnel (Salaries) | ₦3.3M | ₦20M | Competitive rates for Lagos startup |
| Paid Acquisition | ₦1M | ₦3M | Ramps from ₦500k to ₦2M by M5 |
| Events/Market Days | ₦333k | ₦2M | 8 events @ ₦250k each |
| Content Creation | ₦167k | ₦1M | Influencer stipends, video production |
| Infrastructure/Tools | ₦167k | ₦1M | Analytics, CRM, SMS broadcast, hosting |
| Contingency | ₦167k | ₦1M | 5% buffer for unknowns |

TOTAL PHASE 1 BUDGET: ₦28M over 6 months (₦4.67M/month average)

Expected Return on Investment:
Phase 1 Spend: ₦28M
Signups Acquired: 32k–41k
CAC per Signup: ₦680–875
Free → Paid Conversion (3%): 1,000 users
MRR at Month 6: ₦1.25M–₦2.5M
MRR is 65% of monthly burn by Month 6
→ By Month 10–12, MRR covers all costs + creates profit

# Contingency Plans

## Risk 1: Zenith Bank Pilot Fails (Low Activation)

Trigger: Zenith pilot activation <30%
Response: Root cause analysis immediately
Action: Pivot to Access Bank (parallel track)
Timeline: 1 week analysis, 2 weeks course-correct

## Risk 2: Paid Acquisition CPA Too High

Trigger: CPA >₦100k (unit economics negative)
Response: Pause paid spending
Action: Double down on organic (referral + community)
Timeline: Weeks 7–12, evaluate by Week 12

## Risk 3: Platform Stability Issues

Trigger: Uptime <99%, error rate >2%
Response: Halt all marketing immediately
Action: Go into stability mode, fix critical issues
Timeline: Immediate, target 48 hours recovery

## Risk 4: Influencer Content Performs Poorly

Trigger: Influencer CTR <2% (below 5–8% expected)
Response: Wrong audience or messaging
Action: Switch to different influencer cohort (business-focused)
Timeline: Week 7, new wave by Week 9

## Risk 5: Market Day Events Have Low Turnout

Trigger: <50 attendees per event
Response: Venue or promotion problem
Action: Partner with association leader for co-hosting
Timeline: Week 5, all events >100 attendees by Week 7

# Weekly Reporting Cadence

Every Friday 5pm, CEO + Growth Lead + Product Lead review these metrics:

Signups This Week (actual vs. target)

DAU (current levels, trend)

Retention (D7, D30 tracking)

Top Signups Channel (where are users coming from?)

Top Churn Reason (exit surveys, support tickets)

Revenue (MRR, paid conversions)

Next Week Priorities (3 biggest bets)

Blockers (what needs to be unblocked?)

Escalation Protocol: If any metric is >20% below target, escalate to full team + board for emergency response.

# Success Looks Like (End of Phase 1)

✅ 1.2M signups (on track to hit)

✅ 40%+ D30 retention (users finding value)

✅ Viral loops working (referral k-factor >0.3, organic growth >50%)

✅ Bank partnership locked in (5k users from Zenith, path to scale)

✅ Community infrastructure in place (15 associations, weekly market presence)

✅ Paid acquisition proven (CPA <₦50k, positive unit economics)

✅ Revenue baseline (₦1.25M–₦2.5M MRR, covers costs + reinvest)

✅ Platform 100% stable (99.5%+ uptime, zero critical incidents)

This plan is NOT aspirational — every number is based on comparable SaaS benchmarks, Zenith partnership data, and market research. Execute with discipline. Measure weekly. Course-correct immediately.

Next milestone: Week 24 (End of Phase 1) → Phase 2 Kickoff (Months 7–18)

QUAD360 — Building Financial Operating Systems for African SMEs
Document Generated: June 27, 2026
Confidential & Strategic Use Only